## HOW TO USE
PBMM Gap Analysis — How This Works
What This Is | This workbook sits on top of the Master Tracker and the 21 technology workbooks. It reads the control statuses LIVE and tells you where the gaps are, how big they are, and gives you a place to document what to do about them.
No Manual Input Needed | The EXECUTIVE DASHBOARD and GAPS BY FAMILY tabs are 100% formula-driven from the Master Tracker. As your team updates status dropdowns in the technology workbooks, the tracker updates, and this workbook updates. No maturity scores, no subjective ratings, no double-entry.
EXECUTIVE DASHBOARD | One row per technology. Total controls, Passed, In Progress, Failed, Not Started — all pulled live. % Complete and RAG status calculated automatically. RED = below 50%, AMBER = 50-89%, GREEN = 90%+. Bottom section shows totals and how many technologies are at each RAG level.
GAPS BY FAMILY | Heatmap showing the gap RATE (not count) for each Technology × Control Family intersection. A cell showing 100% means every control in that family for that technology has a gap. 0% means fully covered. Red = high gap rate, green = low. Blank = that family doesn't apply to that technology.
REMEDIATION PLAN | This is where you do the actual work. One row per finding. Document: what control failed, which technology, what's missing, what the risk is, what to do about it, who owns it, and when it's due. Priority dropdown (Critical/High/Medium/Low) and Status dropdown (Not Started/In Progress/Completed/Deferred/Waived). 100 rows pre-formatted. The REMEDIATION SUMMARY tab counts from here automatically.
REMEDIATION SUMMARY | Counts from the Remediation Plan automatically. Shows: how many findings by priority, how many completed vs remaining, % remediated overall, and a per-technology breakdown of open Critical and High items. This is your weekly remediation status view.
SharePoint Setup | Place this file in the SAME SharePoint library as the Master Tracker and all 21 workbooks. Open from SharePoint, click Update Links. The EXECUTIVE DASHBOARD and GAPS BY FAMILY tabs will populate live.

## EXECUTIVE DASHBOARD
PBMM Gap Analysis — Executive Dashboard (LIVE from Tracker)
Technology | Total | Passed | In Progress | Failed | Not Started | % Complete | RAG
Analytics
Compute
Containers
Database
Developer Tools
DevOps
Documentation
Hybrid + Multicloud
Identity
Management and Governance
Microsoft-Descoped
Networking
Palo Alto Firewalls
Panorama
Security
ServiceNow
Storage
Tenable Nessus
Tenable Security Centre+
Virtual Desktop Infrastructure
Web
TOTALS
Total Controls
Technologies at RED (< 50% complete)
Technologies at AMBER (50-89% complete)
Technologies at GREEN (90%+ complete)

## GAPS BY FAMILY
Gap Rate by Technology × Control Family (LIVE — lower is better)
Technology | AC | AT | AU | CA | CM | CP | IA | IR | MA | MP | PE | PL | PS | RA | SA | SC | SI
Analytics
Compute
Containers
Database
Developer Tools
DevOps
Documentation
Hybrid + Multicloud
Identity
Management and Governance
Microsoft-Descoped
Networking
Palo Alto Firewalls
Panorama
Security
ServiceNow
Storage
Tenable Nessus
Tenable Security Centre+
Virtual Desktop Infrastructure
Web

## REMEDIATION PLAN
Remediation Action Plan — Gap Closure
# | Control ID | Family | Technology | Finding (What's Missing) | Risk / Impact | Remediation Action | Priority | Owner | Target Date | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## REMEDIATION SUMMARY
Remediation Progress — Summary
By Priority
Priority | Total | Completed | Remaining
Critical
High
Medium
Low
TOTAL
By Status
Not Started
In Progress
Completed
Deferred
Waived
% Remediated
By Technology — Open Items
Technology | Critical | High | Medium + Low
Analytics
Compute
Containers
Database
Developer Tools
DevOps
Documentation
Hybrid + Multicloud
Identity
Management and Governance
Microsoft-Descoped
Networking
Palo Alto Firewalls
Panorama
Security
ServiceNow
Storage
Tenable Nessus
Tenable Security Centre+
Virtual Desktop Infrastructure
Web